## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-06-h-quackers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Customer/Owner, I want to be able to view this page first and log in before being sent to my shopping cart and the catalog OR accessing admin tools depending on privileges. | **Given** I am in a browser **when** I submit a GET request to http://localhost:8080/login **then** I expect to see the log in page. | Pass | Mason Bausenwein; March 16th
| **Given** I press the submit button **when** I have an admins login information in the input boxes **then** I expect to be redirected to the inventory management dashboard | Pass | Mason Bausenwein; March 16th
| **Given** I press the submit button **when** I have anything that is not admin entered in the username box **then** I expect to be redirected to the product view dashboard | Pass | Mason Bausenwein; March 18th
| **Given **I press the submit button **when** account information is entered **then** I expect the account information to stay in the session (basically, have account information present on the page) | Pass | Mason Bausenwein; March 16th
| **Given **I press the register button **when **account information is entered and doesn't exist already, **then **I expect the account to be registered to the database and have a feedback message appear saying account was created. | Pass | Mason Bausenwein; March 16th
| **Given **I press the register button **when **account information is entered and does exist already, **then **I expect the account to not be registered to the database and have a feedback message appear saying there was an error registering the account. | Pass | Mason Bausenwein; March 16th
As a USER I want to HAVE MY DATA PERSIST BETWEEN PAGES so that I DONT HAVE TO LOGIN EVERY TIME | **Given** I AM LOGGED IN **when** I CHANGE PAGES **then** I EXPECT MY DATA TO PERSIST | Pass | Mason Bausenwein; March 16th
| **Given** I AM LOGGED IN **when** I LOG OUT **then** I EXPECT MY DATA TO NO LONGER PERSIST | Pass | Mason Bausenwein; March 16th
| **Given** I HAVE AN ACCOUNT **when** I LOG IN **then** MY DATA SHOULD APPEAR ON SCREEN | Pass | Mason Bausenwein; March 16th; I am assuming data to pertain to admin status and shopping cart information.
As an owner I want to create be able to create a product so that my customers are able to buy it. | **Given** I am an owner **when** I go to the product creation page (http://localhost:4200/inventory/product) **then** I expect to see a form that I can fill out that allows me to input all of the necessary information (i.e. name, size, etc -- NOT ID) | Pass | Mason Bausenwein; March 16th
| **Given** I am a buyer **when** I go to the product creation page (http://localhost:4200/inventory/product) **then** I expect to see an error pop up and be redirected to the login page. | Pass | Mason Bausenwein; March 16th
As an OWNER I want to be able to modify products so that I can change the price, quantity available, name, etc of my items. | **Given** I am an owner **when** I go to the product management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see all of the fields I can modify and a save button | Pass | Mason Bausenwein; March 16th
| **Given** I am a buyer **when** I go to the inventory management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see an error pop up and be redirected to the login page. | Pass | Mason Bausenwein; March 16th
| **Given** I am an owner **when** I hit the submit button on a product management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see a success message. | Pass | Mason Bausenwein; March 16th
As an OWNER I want to SEE PRODUCTS ON THE INVENTORY MANAGEMENT PAGE so that I CAN SELECT THEM TO MODIFY. | **Given** I am an owner **when** I go to the inventory management page (http://localhost:4200/inventory/) **then** I expect to see a list of products that I can modify/add/remove | Pass | Mason Bausenwein; March 16th
| **Given** I am a buyer **when** I go to the inventory management page (http://localhost:4200/inventory/) **then** I expect to see an error pop up and be redirected to the customer product view page. | Pass | Mason Bausenwein; March 16th
| **Given** I am an owner **when** I click the remove button **then** I expect the product to be deleted and to see a success notification if successful or an error notification if not | Pass | Mason Bausenwein; March 16th
As a BUYER I want to BE ABLE TO VIEW MY SHOPPING CART so that ADD/REMOVE ITEMS FROM MY CART AND BUY THEM. | **Given** I am logged in as a buyer and I am on a browser **when** I click the shopping cart button or submit a get request to http://localhost:8080/shoppingcart **then** I expect to see my shopping cart. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
| **Given** I am logged in as a owner and I am on a browser **when** I submit a get request to http://localhost:8080/shoppingcart **then** I expect to see an error pop up and be redirected to the inventory management page. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
As an BUYER I want to SEE PRODUCTS ON THE CATALOG PAGE so that I ADD THEM MY SHOPPING CART. | **Given** I am an buyer and I want to browse the products **when** I go to the catalog page (http://localhost:4200/catalog/) **then** I expect to see a list of products that I can add to cart/see details | Pass | Mason Bausenwein; March 18th
| **Given** I am an buyer and I want to add one product into my shopping cart **when** I click Add to Cart button **then** I expect to a confirm notification | Pass | Mason Bausenwein; March 18th
| **Given** I am an buyer and I want to see my shopping cart **when** I click Go to Cart button **then** I expect to go to http://localhost:4200/cart | Pass | Mason Bausenwein; March 18th
| **Given** I am logged in as an owner (or I am not logged in) and I am on a browser **when** I submit a get request to http://localhost:8080/catalog **then** I expect to be redirected to the login page. | Pass | Mason Bausenwein; March 18th
As a BUYER I want to BE ABLE TO SEARCH THE PRODUCT PAGE so that I CAN VIEW PRODUCTS WITH SPECIFIC NAME. | **Given** I am a buyer and I want to search a product with specific name **when** I entered the key work to the search bar **then** I expect to see a list of product names that match the keyword. | Pass | Mason Bausenwein; March 18th
| **Given** I am a buyer and I want to see the product detail **when** I click the result name **then** I expect to go to the product detail page. | Pass | Mason Bausenwein; March 18th
As a BUYER I want to SEE THE PRODUCT DETAILS so that I CAN LEARN MORE ABOUT THE PRODUCT. | **Given** I am a buyer and I want to see product detail **when** I click the Detail button **then** I expect to see a product details page. | Pass | Mason Bausenwein; March 18th
| **Given** I am a buyer and I want to add products to shopping cart **when** I set the quantity and click the Add to Cart button **then** I expect to see a confirm notification. | Pass | Mason Bausenwein; March 18th
| **Given** I am a buyer and I want to go back to the catalog page **when** I click the Go Back button **then** I expect to go to http://localhost:4200/catalog | Pass | Mason Bausenwein; March 18th
| **Given** I am an buyer and I want to see my shopping cart **when** I click Go to Cart button **then** I expect to go to http://localhost:4200/cart | Pass | Mason Bausenwein; March 18th
| **Given** I am an owner or not logged in **when** I go to http://localhost:4200/catalog/:id **then** I expect to be redirected to the login page and told I am not authorized | Pass | Mason Bausenwein; March 18th
As a BUYER I want to BE ABLE TO ADD PRODUCTS TO SHOPPING CART so that I CAN CHECKOUT. | **Given** I am logged in a buyer and I am on catalog page **when** I click on the add to cart button **then** I expect to add one product into my shopping cart. | Pass | Mason Bausenwein; March 18th
| **Given** I am logged in a buyer and I am on detail page **when** I set the quantity and click on the add to cart button **then** I expect to add the quantity of products I want to my cart. | Pass | Mason Bausenwein; March 18th
As a BUYER/OWNER I want to SEE A NAV BAR AT THE TOP OF THE WEBSITE so that I CAN EASILY SWITCH BETWEEN PAGES. | **Given** I am on the website **when** I go to any page on the website **then** I should see a nav bar containing links to the other pages | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am on the website **when** I am an owner **then** I should NOT see the shopping cart button and SHOULD see an inventory management button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am on the website **when** I am a buyer **then** I SHOULD see the shopping cart button and SHOULD NOT see an inventory management button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a BUYER I want to HAVE A PROFILE PAGE so that I CAN SAVE MY PAYMENT AND SHIPPING INFORMATION. | **Given** I am an owner or not logged in **when** I attempt to access my profile page **then** I expect to be redirected to the login screen and see an error | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am a buyer **when** I attempt to access my profile page **then** I expect to see a screen where I can save my payment and shipping information along with a save button and a clear button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a BUYER I want to HAVE A PROFILE PAGE so that I CAN SAVE MY PAYMENT AND SHIPPING INFORMATION. | **Given** I am an owner or not logged in **when** I attempt to access my profile page **then** I expect to be redirected to the login screen and see an error | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am a buyer **when** I attempt to access my profile page **then** I expect to see a screen where I can save my payment and shipping information along with a save button and a clear button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a CUSTOMER I want to SEE A RECEIPT OF THE ITEMS I PURCHASED so that I CAN MAKE SURE I BOUGHT EVERYTHING I WANT | **Given** I am on the shopping cart page **when** I click checkout **then** I expect to be redirected to this page. | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** all of the items I wanted were in the inventory **when** I clicked checkout **then** I expect to see a success message with the items I bought and their total price | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** all of the items I wanted were NOT in the inventory **when** I clicked checkout **then** I expect to see an error message stating what items were unavailable | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2