## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-06-h-quackers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Customer/Owner, I want to be able to view this page first and log in before being sent to my shopping cart and the catalog OR accessing admin tools depending on privileges. | **Given** I am in a browser **when** I submit a GET request to http://localhost:8080/login **then** I expect to see the log in page. | Pass | Mason Bausenwein; March 16th
| **Given** I press the submit button **when** I have an admins login information in the input boxes **then** I expect to be redirected to the inventory management dashboard | Fail | Mason Bausenwein; March 16th; does not redirect to inventory management page - Awaiting Merge of inventoryPage Branch
| **Given** I press the submit button **when** I have anything that is not admin entered in the username box **then** I expect to be redirected to the product view dashboard | Fail | Mason Bausenwein; March 16th; does not redirect to product catalog - Awaiting completion of catalog page
| **Given **I press the submit button **when** account information is entered **then** I expect the account information to stay in the session (basically, have account information present on the page) | Pass | Mason Bausenwein; March 16th
| **Given **I press the register button **when **account information is entered and doesn't exist already, **then **I expect the account to be registered to the database and have a feedback message appear saying account was created. | Pass | Mason Bausenwein; March 16th
| **Given **I press the register button **when **account information is entered and does exist already, **then **I expect the account to not be registered to the database and have a feedback message appear saying there was an error registering the account. | Pass | Mason Bausenwein; March 16th
As a USER I want to HAVE MY DATA PERSIST BETWEEN PAGES so that I DONT HAVE TO LOGIN EVERY TIME | **Given** I AM LOGGED IN **when** I CHANGE PAGES **then** I EXPECT MY DATA TO PERSIST | Pass | Mason Bausenwein; March 16th
| **Given** I AM LOGGED IN **when** I LOG OUT **then** I EXPECT MY DATA TO NO LONGER PERSIST | Pass | Mason Bausenwein; March 16th
| **Given** I HAVE AN ACCOUNT **when** I LOG IN **then** MY DATA SHOULD APPEAR ON SCREEN | Pass | Mason Bausenwein; March 16th; I am assuming data to pertain to admin status and shopping cart information.
As an owner I want to create be able to create a product so that my customers are able to buy it. | **Given** I am an owner **when** I go to the product creation page (http://localhost:4200/inventory/product) **then** I expect to see a form that I can fill out that allows me to input all of the necessary information (i.e. name, size, etc -- NOT ID) | Fail | Mason Bausenwein; March 16th; no product information page on main - Awaiting Merge of inventoryPage Branch
| **Given** I am a buyer **when** I go to the product creation page (http://localhost:4200/inventory/product) **then** I expect to see an error pop up and be redirected to the login page. | Fail | Mason Bausenwein; March 16th; no product information page on main - Awaiting Merge of inventoryPage Branch
As an OWNER I want to be able to modify products so that I can change the price, quantity available, name, etc of my items. | **Given** I am an owner **when** I go to the product management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see all of the fields I can modify, a save button, and a delete button | Fail | Mason Bausenwein; March 16th; no product management page on main - Awaiting Merge of inventoryPage Branch
| **Given** I am a buyer **when** I go to the inventory management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see an error pop up and be redirected to the login page. | Fail | Mason Bausenwein; March 16th; no product management page on main - Awaiting Merge of inventoryPage Branch
| **Given** I am an owner **when** I hit the submit button on a product management page (http://localhost:4200/inventory/product/{id}) **then** I expect to see a success message. | Fail | Mason Bausenwein; March 16th; no product management page on main - Awaiting Merge of inventoryPage Branch
As an OWNER I want to SEE PRODUCTS ON THE INVENTORY MANAGEMENT PAGE so that I CAN SELECT THEM TO MODIFY. | **Given** I am an owner **when** I go to the inventory management page (http://localhost:4200/inventory/) **then** I expect to see a list of products that I can modify/add/remove | Fail | Mason Bausenwein; March 16th; no inventory management page on main - Awaiting Merge of inventoryPage Branch
| **Given** I am a buyer **when** I go to the inventory management page (http://localhost:4200/inventory/) **then** I expect to see an error pop up and be redirected to the customer product view page. | Fail | Mason Bausenwein; March 16th; no inventory management page on main - Awaiting Merge of inventoryPage Branch
| **Given** I am an owner **when** I click the remove button **then** I expect the product to be deleted and to see a success notification if successful or an error notification if not | Fail | Mason Bausenwein; March 16th; no inventory management page on main - Awaiting Merge of inventoryPage Branch
As a BUYER I want to BE ABLE TO VIEW MY SHOPPING CART so that ADD/REMOVE ITEMS FROM MY CART AND BUY THEM. | **Given** I am logged in as a buyer and I am on a browser **when** I click the shopping cart button or submit a get request to http://localhost:8080/shoppingcart **then** I expect to see my shopping cart. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
| **Given** I am logged in as a owner and I am on a browser **when** I submit a get request to http://localhost:8080/shoppingcart **then** I expect to see an error pop up and be redirected to the inventory management page. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
As a BUYER I want to BE ABLE TO VIEW THE PRODUCT PAGE so that I CAN VIEW PRODUCTS AND ADD THEM TO MY CART. | **Given** I am logged in a buyer and I am on a browser **when** I submit a get request to http://localhost:8080/products **then** I expect to see a list of products. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
| **Given** I am logged in as an owner (or I am not logged in) and I am on a browser **when** I submit a get request to http://localhost:8080/products **then** I expect to be redirected to the login page. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
| **Given** I am logged in a buyer and I am on a browser **when** I type in the search box **then** I expect to see the list of products change based on my query. | Fail | Mason Bausenwein; March 16th; Awaiting Implementation
As a BUYER/OWNER I want to SEE A NAV BAR AT THE TOP OF THE WEBSITE so that I CAN EASILY SWITCH BETWEEN PAGES. | **Given** I am on the website **when** I go to any page on the website **then** I should see a nav bar containing links to the other pages | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am on the website **when** I am an owner **then** I should NOT see the shopping cart button and SHOULD see an inventory management button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am on the website **when** I am a buyer **then** I SHOULD see the shopping cart button and SHOULD NOT see an inventory management button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a BUYER I want to HAVE A PROFILE PAGE so that I CAN SAVE MY PAYMENT AND SHIPPING INFORMATION. | **Given** I am an owner or not logged in **when** I attempt to access my profile page **then** I expect to be redirected to the login screen and see an error | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am a buyer **when** I attempt to access my profile page **then** I expect to see a screen where I can save my payment and shipping information along with a save button and a clear button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a BUYER I want to HAVE A PROFILE PAGE so that I CAN SAVE MY PAYMENT AND SHIPPING INFORMATION. | **Given** I am an owner or not logged in **when** I attempt to access my profile page **then** I expect to be redirected to the login screen and see an error | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** I am a buyer **when** I attempt to access my profile page **then** I expect to see a screen where I can save my payment and shipping information along with a save button and a clear button | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
As a CUSTOMER I want to SEE A RECEIPT OF THE ITEMS I PURCHASED so that I CAN MAKE SURE I BOUGHT EVERYTHING I WANT | **Given** I am on the shopping cart page **when** I click checkout **then** I expect to be redirected to this page. | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** all of the items I wanted were in the inventory **when** I clicked checkout **then** I expect to see a success message with the items I bought and their total price | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2
| **Given** all of the items I wanted were NOT in the inventory **when** I clicked checkout **then** I expect to see an error message stating what items were unavailable | Fail | Mason Bausenwein; March 16th; Will not be implemented in Sprint 2